## Multiple Estimators
Section 1: Estimator Input Matrix | Name / Role | Optimistic (O) | Most Likely (M) | Pessimistic (P) | PERT Estimate (O+(4*M)+P)/6
Estimator 1 | Programme Manager | 10 | 14 | 22 | 14.6667
Estimator 2 | Lead SME | 12 | 15 | 24 | 16
Estimator 3 | Junior SME | 8 | 18 | 30 | 18.3333
Calculated Baseline Group Averages | Simple Average (Raw Inputs): | 10 | 15.6667 | 25.3333 | 16.3333
Section 2: PERT Baseline Analytics | Metric Name | Formula Result | Description
- | Group Expected Value (E) | 16.3333 | Average expected task duration
- | Group Baseline Std Dev (σ) | 2.5556 | Average baseline uncertainty for 1 estimator
Section 3: Target Effort Simulation | Target Hours to complete task: | 17.9667 | <- Edit this number to change target hours
|  | 95% | <- Set Desired Confidence Interval
| Normal Distribution Facts | Probability | # Standard Errors
|  | 68.2% | 1
|  | 90% | 1.64
|  | 95% | 1.96
|  | 99.7% | 3 |  | 1.96
Section 4: Group Scaling Matrix | Number of Estimators (n) | Combined Standard Error | Lower Bound | Upper Bound | Probability of Hitting Target (C11)
| 1 | 2.5556 | 11.3244 | 21.3422 | 73.86%
| 3 | 1.4755 | 13.4414 | 19.2252 | 86.59%
| 5 | 1.1429 | 14.0933 | 18.5734 | 92.35%
| 10 | 0.80814 | 14.7494 | 17.9173 | 97.84%

## Weighted and Multiple
Section 1: Estimator Matrix | Role | Weight | Optimistic Estimate | Most Likely Estimate | Pessimistic Estimate | Weighted Optimistic | Weighted Most Likely | Weighted Pessimistic
Estimator 1 (Senior) | Lead Dev | 5 | 10 | 14 | 22 | 50 | 70 | 110
Estimator 2 (Senior) | Arch | 4 | 12 | 15 | 24 | 48 | 60 | 96
Estimator 3 (Junior) | Junior | 1 | 8 | 18 | 30 | 8 | 18 | 30
Calculated Task Averages | Total Weight: | 10 | 10 | 15.6667 | 25.3333 | 10.6 | 14.8 | 23.6
Section 2: Baseline Analytics | Expected Value (E) | Std Dev (σ) | - | - | - | - | - | -
Unweighted (Simple Avg) Baseline | 16.3333 | 2.5556 | - | - | - | - | - | -
Weighted Baseline | 15.5667 | 2.1667 | - | - | - | - | - | -
Section 3: Group Scaling Matrix |  | Estimators (n) | Unweighted Standard Error | Unweighted 95% Lower | Unweighted 95% Upper | Weighted Standard Error | Weighted 95% Lower | Weighted 95% Upper
Group Scaling Row 1 |  | 1 | 2.5556 | 11.3244 | 21.3422 | 2.1667 | 11.32 | 19.8133
Group Scaling Row 2 |  | 3 | 1.4755 | 13.4414 | 19.2252 | 1.2509 | 13.1149 | 18.0185
Group Scaling Row 3 |  | 5 | 1.1429 | 14.0933 | 18.5734 | 0.96896 | 13.6675 | 17.4658
Group Scaling Row 4 |  | 10 | 0.80814 | 14.7494 | 17.9173 | 0.68516 | 14.2238 | 16.9096